## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Sprint Review
As a user of DGS I need to use the system to insert start date, end date and on the system, also LogIdUser, so I can save a registry of these activities | Task 1 - Call SP from VB 8 hrs | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 2 - Call SP From view | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 3 - Create Model from UI | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 4 - Create github source | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 5 - Burn down chart creation | Luis | Closed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 6 - Sprint retrospective | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 7 - Create View to insert data 1 a | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 8 - Create View to insert data 1 b | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 9 - Create View to insert data 1 c | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 10 - Create View to insert data 1 d | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 11 - Create View to insert data 1 e | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 12 - Sprint backlog creation | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 13 - Daily scrum | Luis | Closed | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 14 - Sprint review | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 15 - Sprint retrospective | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 16 - Sprint Planning | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 17 - Project Creation | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 38 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal