## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Sprint Review
As a user of DonBest I need to use the system to insert start date, end date and on the system, also LogIdUser, so I can save a registry of these activities | Task 1 - Call SP from VB 8 hrs | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 2 - Call SP From view | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 3 - Create Model from UI | Luis | Closed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 4 - Create github source | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 5 - Burn down chart creation | Luis | Closed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 6 - Sprint retrospective | Luis | Closed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 7 - Create View to insert data | Luis | Closed | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 70 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal